## 1. Overview
Bac II — system delivery plan
14 Aug – 03 Sep 2026 · 15 working days · two parallel tracks
Position
The application is built — frontend, database, API, authentication, exam engine, marking engine and tutor are all in place. What is missing is content and proof: no exam questions have been extracted, nothing has been indexed for search, and the marking has never been checked against a teacher. This plan closes both gaps in three weeks across two tracks that run side by side.
The datasets
What the system is built on, and the state of each one today.
The two tracks
Track | Scope | Areas | Days | Inventory
Track A — Data & AI | Fills the library and proves the answers | Embeddings · Question extraction · OCR · Chunking · Retrieval · Grading | 15 | Dataset | What it is | Size
Track B — Platform | Makes it deployable, secure and tested | Database · Backend · Frontend · Auth · Infrastructure · Testing | 13 | Past exam papers | Real Baccalaureate examinations as sat, published by the ministry, most with the official marking scheme. All four branches, both sessions per year. | 1,451 papers · 7,472 pages 2004–2021 · 110 sessions
|  |  |  | — by branch | Literature & Humanities 520 · General Sciences 430 · Life Sciences 258 · Sociology & Economics 243. | 1,451 papers
Headline |  |  |  | — by format | 1,382 are digital PDFs with extractable text. 69 are scans requiring OCR and confidence gating before any extraction. | 1,382 digital · 69 scanned
Start | Friday 14 August 2026 |  |  | — with marking schemes | Papers carrying the official barème. These are what make defensible marking possible; the rest still yield questions and model answers. | 459 papers
Finish | Thursday 03 September 2026 |  |  | — subjects | Mathematics, Physics, Chemistry, Biology, Philosophy, Arabic, French, English, History, Geography, Economics, Sociology, Civics — in Arabic, French and English versions. | ~15 subject areas × 3 languages
Working days | 15 calendar working days |  |  | — known gap | No papers for the 2010, 2014 or 2020 sessions. 15 of 18 years covered. | 3 years missing
Effort | 28 developer-days across two tracks |  |  | CRDP textbooks | The official course books, already transcribed to machine-readable text with mathematics as LaTeX and Arabic/French as Unicode. Every chapter carries the PDF page range it was read from, so any citation traces to a real page. | 38 books · 9,593 pages
Team assumed | Two developers, one per track. Track B finishes 2 days early and can support Track A |  |  | Curriculum map | Subjects, units and chapters parsed out of the textbooks' own contents pages by a regex parser — deliberately not a model, so the result is reproducible and reviewable. | 577 chapters GS 148 · LS 190 · SE 127 · LH 112
Code already written | Frontend · Backend · Database · Auth · Exam engine · Marking engine · Tutor |  |  | Student work | Attempts, answers and photographed scripts. Feeds grading calibration and, at volume, difficulty recalibration. | None yet
Nothing written yet | Embeddings · Question extraction · Chunking · Infrastructure |  |  | Sample handwritten scripts | Needed to prove the photo → OCR self-consistency gate → marking path on real Lebanese handwriting. | ~20–30 needed
Why built areas still carry days | Written is not the same as proven: none has met real content, real scale or a second instance
Legend
Dependencies outside the team |  |  |  | Done / verified
AI provider key | Track A cannot start without it. |  |  | In progress / awaited
One teacher, one day | Grading calibration cannot be proved without independent marks. |  |  | Gap or blocker
Hosting decision | Infrastructure work needs a target platform chosen. |  |  | Informational

## 2. Workstreams
Workstreams — major steps by area
Track | Area | Major steps | Code | Status | Days | Start | Finish | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 01 | 02 | 03
A | Embeddings | Provider configured Backfill every row Coverage verified | NONE | NOT STARTED | 2 | 14 Aug | 17 Aug
A | Question extraction | Single-paper validation Sample gate — 40 papers Bulk run Failure reconciliation | NONE | NOT STARTED | 5 | 18 Aug | 24 Aug
A | OCR | Vendor routing Confidence gating Merge into extraction | BUILDING | WIRED — UNTESTED | 2 | 25 Aug | 26 Aug
A | Chunking | Textbooks to course chunks Chunk embedding Per-chapter coverage | NONE | NOT STARTED | 2 | 27 Aug | 28 Aug
A | Retrieval | Eval harness on real corpus Tier threshold tuning Refusal-rate check | BUILT | BUILT — UNTUNED | 2 | 31 Aug | 01 Sep
A | Grading | Run against known marks Criterion-level agreement Unmarkable path verified | BUIlLDING | WIRED — UNCALIBRATED | 2 | 02 Sep | 03 Sep
B | Database | Vector width and index check Schema ready for bank volume Query plans at real scale | BUILT | BUILT — UNVERIFIED AT SCALE | 1 | 14 Aug | 14 Aug
B | Backend / API | Route audit Rate limiter moved off in-process Error and audit logging | BUILT | BUILT — SINGLE INSTANCE | 2 | 17 Aug | 18 Aug
B | Frontend | Real content through every screen Empty, loading and error states Responsive and accessibility pass | BUILT | BUILT — DEMO DATA ONLY | 2 | 19 Aug | 20 Aug
B | Auth & accounts | Demo credentials removed Session revocation verified Admin actions audited | BUILT | BUILT — DEMO CREDENTIALS | 1 | 21 Aug | 21 Aug
B | Infrastructure | Managed database and storage Secrets and environment Scheduled jobs, backups, monitoring | NONE | NOT STARTED | 4 | 24 Aug | 27 Aug
B | Testing & QA | Automated suites green Integration and load Security and UAT | BUILDING | PARTIAL | 3 | 28 Aug | 01 Sep
Track A 15 days · Track B 13 days · 15 working days, 14 Aug – 03 Sep · Track B carries 2 days of slack

## 3. Testing
Testing
What gets tested, when it runs, and what counts as passing.
Principles
Three rules shape everything below. A wrong answer is worse than no answer, so retrieval is measured on false answers rather than coverage. A mark that cannot be explained is not a mark, so grading is proved against a human rather than asserted. And anything that cannot be measured is reported as unknown rather than assumed to pass.
Test coverage
Layer | What it covers | When it runs | Passes when
Unit tests | Scoring, marking, scheduling logic | Continuous | Green on every commit. No database or provider key required to run.
Static and data audit | Dead code, unread translation keys, unreachable routes, null embeddings, MCQs with no correct option, barèmes with no solution | Daily | Zero blocking findings. Every remaining finding explained or by design.
Integration / smoke | End-to-end HTTP checks against a running server | Every deploy | All routes answer. Signup, practice, exam and chat paths complete.
Retrieval evaluation | Precision and recall per tier against the real corpus | After corpus build, then weekly | Measured false-answer rate below target. A wrong answer is worse than a refusal.
Grading calibration | System marks versus a teacher's marks on the same scripts | Once before pilot, then per term | Criterion-level agreement measured and published. Disagreements explained.
OCR gates | Confidence, page count, repetition loops, normalisation flags | Every scanned document | No page passes downstream unflagged. Page-count mismatch blocks the document.
Load and performance | Retrieval latency, concurrent exam sittings, batch throughput | Before pilot | Retrieval p95 within budget. Timer stays server-authoritative under load.
Security | Session revocation, file ownership, rate limits, payment surface | Before pilot | Sessions killable mid-exam. No public file URLs. No card data stored.
Accessibility and UX | Contrast, colour-independence, reduced motion | Before pilot | Status never carried by colour alone. Motion preference respected.
User acceptance | Real students and one teacher on real papers | Pilot | Task completion without assistance. Marks accepted as fair.
Regression | Full suite plus audit before hand-off | End of sprint | Everything above green, or the exception is written down.
Gates — work stops here until these pass
Extraction sample gate | Measured on 40 papers before the bulk run is committed. If accuracy is below target the pipeline is fixed first — the alternative is a question bank nobody can trust.
Retrieval false-answer rate | Measured before the tutor is opened to students. A confident answer from the wrong chapter is the failure mode that matters.
Grading agreement | Measured against a teacher before any mark is shown to a student.
Security and revocation | Verified before the pilot: sessions killable mid-exam, no public file URLs, no card data stored.