## 1. Executive summary
Bac II — AI delivery plan
The remaining artificial-intelligence work, in the order it must happen. Prepared 14 August 2026.
The position in one paragraph
The software is built and working. The content is not. The system knows the official Lebanese curriculum — 577 chapters read out of 38 CRDP textbooks — but it has not yet read a single past exam paper, and nothing has been indexed for search. That is why the tutor currently declines every question: not a fault, but an empty library. The plan below fills the library, proves the marking against a real teacher, and turns the product on.
Headline numbers
Working days of AI work | 64 days
Calendar duration, one developer | ~13 weeks
Planned start | 17 Aug 2026
Planned finish | 12 Nov 2026
Delivery margin already included | +17 days (one per task)
Past exam papers to process | 1,451 papers · 7,472 pages
Textbook pages to process | 9,593 pages · 38 books
Open blockers requiring a decision | 3
The nine phases
Phase | What it delivers | Days | Finishes
A · Search foundation | The system can search its own material at all | 4 | 20 Aug
B · Question bank | A question bank built from 20 years of real exams | 25 | 24 Sep
C · Course material | Teaching material for every chapter of the programme | 8 | 06 Oct
D · Answer quality | Proof the tutor finds the right material, measured not assumed | 4 | 12 Oct
E · Tutor live | The tutor answers students — grounded, cited, honest when it cannot | 2 | 14 Oct
F · Marking | Marking that agrees with a real teacher, including handwriting | 7 | 23 Oct
G · Practice & personalisation | Unlimited fresh practice, and difficulty learned from real students | 5 | 30 Oct
H · Real exam structure | Feedback per step of an exercise, not just a total mark | 5 | 06 Nov
I · Efficiency | The same quality, measurably cheaper and faster to run | 4 | 12 Nov
The three blockers — decisions we need
1. An AI provider key | The product cannot be shown to anyone honestly until this is in place. Cost: negligible. | Stops the very first task, and therefore all 17.
2. Mark per part, or per exercise? | Marking each part separately means five AI calls per exercise instead of one — a fivefold difference in what marking costs to run every day, for near-identical feedback. Recommendation: one call per exercise. | Stops task H1.
3. One teacher, for one day | We need a human to mark the same scripts independently so we can prove our marks match theirs. Without it we would be shipping marks nobody has checked. | Stops task F1.
How to read the day counts
Every task carries one extra day beyond the estimate, deliberately, as delivery margin — 47 days of work is scheduled as 64. Days are whole working days for one developer, Monday to Friday. Tasks are scheduled back to back; the finish date assumes no parallel work and no waiting on the three blockers above. Every task listed has a defined deliverable — the 'what done looks like' column on the timeline sheet — so completion is observable rather than reported.

## 2. Timeline
Timeline — every task, in delivery order
ID | Phase | Task | What 'done' looks like | Est. | Margin | Days | Start | Finish | Dependency / blocker | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
A1 | A | Configure the embedding provider | A working API key in the environment; a test index written and read back | 1 | +1 | 2 | 17 Aug | 18 Aug | BLOCKER: API key not provided
A2 | A | Index all existing content | Every question and course chunk in the database carries a search fingerprint; the audit reports zero gaps | 1 | +1 | 2 | 19 Aug | 20 Aug | Follows A1 | bar: W1
B1 | B | Supervised trial run on one past paper | One real paper fully converted into questions, model answers and mark schemes, read line by line by a human and signed off | 5 | +1 | 6 | 21 Aug | 28 Aug | Follows A2
B2 | B | Process the 1,382 digital past papers | The full digital archive converted into a searchable question bank with official answers and mark allocations | 8 | +1 | 9 | 31 Aug | 10 Sep | Follows B1 sign-off | bar: W3 to W4
B3 | B | Process the 69 scanned past papers | The scanned minority read by OCR, quality-gated page by page, and merged into the same bank | 3 | +1 | 4 | 11 Sep | 16 Sep | Follows B1 sign-off
B4 | B | Human review of the extracted questions | A sampled review per subject and per year, with corrections applied; error rate recorded | 5 | +1 | 6 | 17 Sep | 24 Sep | Needs a reviewer who knows the syllabus | bar: W5 to W6
C1 | C | Convert the 38 textbooks into teaching material | Every chapter split into self-contained explanations a student can read on their own | 4 | +1 | 5 | 25 Sep | 01 Oct | Follows A2
C2 | C | Index the course material and verify coverage | Every chapter of every subject has retrievable material; chapters with none are listed by name | 2 | +1 | 3 | 02 Oct | 06 Oct | Follows C1 | bar: W7 to W8
D1 | D | Measure retrieval accuracy on the real corpus | A measured report: how often the system finds the right material, and how often it correctly says it cannot | 1 | +1 | 2 | 07 Oct | 08 Oct | Needs B and C complete
D2 | D | Tune the confidence thresholds | Thresholds set from evidence rather than defaults, with the trade-off documented | 1 | +1 | 2 | 09 Oct | 12 Oct | Follows D1 | bar: W8 to W9
E1 | E | End-to-end tutor verification | A tested tutor that answers only from real curriculum material, cites its source, and refuses honestly when the programme does not cover a question | 1 | +1 | 2 | 13 Oct | 14 Oct | Follows D2
F1 | F | Calibrate marking against a teacher | The same scripts marked by the system and by a teacher, differences analysed, prompts adjusted until they agree | 3 | +1 | 4 | 15 Oct | 20 Oct | BLOCKER: needs one teacher for one day | bar: W9 to W10
F2 | F | Validate handwritten answer photos | Real handwritten scripts photographed, read and marked; failure rate measured before students depend on it | 2 | +1 | 3 | 21 Oct | 23 Oct | Needs sample handwritten scripts
G1 | G | Switch on generated practice questions | New practice problems written from real questions, duplicate-checked, independently solved, and released only after human approval | 2 | +1 | 3 | 26 Oct | 28 Oct | Needs someone to staff the approval queue | bar: W11
G2 | G | Calibrate question difficulty from real use | Difficulty derived from how students actually performed, replacing the fixed default; sharpens the predicted mark | 1 | +1 | 2 | 29 Oct | 30 Oct | Needs live students — runs during the pilot
H1 | H | Mark exercises part by part | A student is told which step of an exercise lost the marks, not just the total | 4 | +1 | 5 | 02 Nov | 06 Nov | BLOCKER: decision needed — per part or per exercise | bar: W12
I1 | I | Cost and speed tuning | Same output, measurably cheaper and faster: reused request context, bulk jobs on the half-price channel, right-sized model per job | 3 | +1 | 4 | 09 Nov | 12 Nov | Needs real usage to measure
TOTAL |  |  |  | 47 | +17 | 64 | 17 Aug | 12 Nov | 13 weeks, one developer

## 3. The datasets
The datasets
What the system is being built on, where each one came from, and its state today.
What a 'past paper' is
A past paper is a real Lebanese Baccalaureate examination that was actually sat in a previous year, published afterwards by the Ministry of Education and the CRDP. Each one is a single subject, for a single branch, from a single session — for example "Mathematics, General Sciences, 2017, first session". Most are accompanied by the official marking scheme, or barème: the document that states how many marks each part of each answer is worth. These papers are the most valuable asset in the project, for three reasons. They define what is actually asked. A syllabus states a topic; a past paper shows how that topic is examined in practice — the phrasing, the level of difficulty, how much working is expected. Twenty years of them show which topics recur and which are rare. They carry the official answers. Because the ministry publishes model answers, the system can tell a student what the correct answer is without ever inventing one. Every explanation the tutor gives is traceable to a real document. They carry the official mark allocation. This is what lets us mark a student's written work the way an examiner would — criterion by criterion, against the same barème — rather than guessing at a score. Without the barème there is no defensible mark; with it, every mark we award can be explained and, if contested, reviewed by a human. In short: the past papers are the ground truth of the product. The system is deliberately built so it can only say things it can trace back to them, or to the official textbooks. When it cannot, it says so.
Inventory
Dataset | What it is | Size | State today
Past exam papers | Real Baccalaureate examinations as sat, published by the ministry, most with the official marking scheme. Covers all four branches and both examination sessions per year. | 1,451 papers · 7,472 pages 2004–2021 · 110 sessions | COLLECTED — none processed yet
— by branch | Literature & Humanities 520 · General Sciences 430 · Life Sciences 258 · Sociology & Economics 243. | 1,451 papers | Balanced across branches
— by format | 1,382 are digital PDFs whose text can be read directly. 69 are scans of paper and need optical character recognition before anything can be extracted. | 1,382 digital · 69 scanned | Two processing routes needed
— with marking schemes | Papers that arrived with the official barème attached. These are the ones that let us mark written work the way an examiner does. The rest still give us questions and answers. | 459 papers | The highest-value subset
— subjects covered | Mathematics, Physics, Chemistry, Biology, Philosophy, Arabic, French, English, History, Geography, Economics, Sociology, Civics — each appearing in Arabic, French and English versions. | ~15 subject areas × 3 languages | Complete
— known gap | No papers held for the 2010, 2014 or 2020 sessions. Not fatal — 15 of 18 years are covered — but worth closing if the ministry archive has them. | 3 years missing of 18 | GAP — worth chasing
CRDP textbooks | The official course books the curriculum is taught from. Already transcribed into machine-readable text with the mathematics and Arabic script intact, and every chapter tagged with the book page it came from, so any citation can be traced to a real page. | 38 books · 9,593 pages English, French, Arabic | TRANSCRIBED — not yet split into teaching material
The curriculum map | Every subject, unit and chapter of the programme, read out of the textbooks' own contents pages rather than typed by hand — so it is derived from the official books, not invented. | 577 chapters GS 148 · LS 190 · SE 127 · LH 112 | LOADED — 6 books still to add
Student work | What students write and photograph as they use the product. Feeds the marking calibration and, once there is enough of it, teaches the system which questions are genuinely hard. | None yet | ARRIVES WITH THE PILOT
Sample handwritten scripts | A small set of real handwritten answers, needed to prove the photograph-and-mark path works on Lebanese handwriting before students rely on it. | ~20–30 scripts needed | TO BE COLLECTED
What the AI actually does with each one
Past papers | Reads each paper and pulls out the questions, the official answers and the mark allocation. The result is a searchable bank of real exam questions with real answers.
CRDP textbooks | Splits each chapter into self-contained explanations — a definition, a method, a worked example — so the tutor has something to teach from when a student's question does not match a past exam question.
Both, indexed | Everything is converted into a searchable fingerprint so the system can find the right page for a question in milliseconds.
Student work | Marked against the official scheme, and used to learn which questions are genuinely difficult rather than assuming.