## 1. Scope
Bac II — AI sprint, 3 weeks
17 Aug – 04 Sep 2026 · 15 working days · one developer
The three weeks
Week 1 — Retrieval substrate + pipeline validation | Embedding backend live, all null vectors backfilled, extraction pipeline proven on one paper by hand and hardened, Batch submission path wired.
Week 2 — Corpus build | 1,382 digital papers batch-extracted, 69 scans through the OCR + gates route, 38 textbooks chunked and embedded as tier-2 material.
Week 3 — Quality, activation, calibration | Extraction error rate measured on a stratified sample, retrieval thresholds tuned against a real precision/recall curve, tutor verified end to end, grading calibrated against known marks.
Deferred — not in these 3 weeks
Workstream | What it is | Size | Why it is out
Generated practice problems | Write-from-real-questions, embedding dedupe at 0.95, independent second-model solve, admin approval gate. | ~3 days | Needs the question bank stable first, and someone to staff the review queue.
Per-part marking (exercise structure) | parent_id / part_label / points on questions; composition, marking, mastery, flashcards and tutor context all follow. Blocked on one decision: mark per part (≈20 calls/paper) or per exercise returning marks per part (≈4). Fivefold difference in marking cost. | ~3 days | Schema change plus a decision. Does not belong in a 3-week sprint.
Difficulty recalibration | `npm run ingest -- --recalibrate` recomputes question difficulty from observed attempts, replacing the 0.5 default and sharpening the predicted mark. | ~1 day | Requires live student attempts. Impossible before a pilot.
Cost and latency tuning | Measure cache_read_input_tokens on real traffic, extend prompt caching, right-size the model per job, confirm Batch coverage on every non-interactive path. | ~3 days | Needs real usage to measure against. Guesswork before that.
Blockers
AI provider key — embedding + inference | Stops T1, and therefore all twelve. Nothing in this sprint starts without it.
A teacher, one day, booked for week 3 | T11 cannot be done without independently marked scripts to compare against.
~20–30 sample handwritten scripts | Not on the critical path this sprint, but the photo-and-mark path stays unproven until they exist.

## 2. Task timeline
Task timeline — 12 tasks, 15 working days
Wk | ID | Task | Acceptance criterion | Days | Start | Finish | Parallelism / dependency | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15
1 | T1 | Provision the embedding backend | A round-trip embed → cosine search returns the expected row. `npm run detect:data` reports the vector columns as correctly dimensioned. | 1 | 17 Aug | 17 Aug
1 | T2 | Backfill embeddings across existing rows | `npm run detect:data` returns zero rows with a null vector. Current state: 38 questions and 27 chunks, all null — this is the single fault making the tutor refuse everything. | 1 | 18 Aug | 18 Aug | bar: D2
1 | T3 | Supervised trial: one paper end to end | One paper in the database whose questions, solutions and barèmes match the PDF exactly. Every schema violation and mis-segmentation logged as a prompt or parser defect. | 2 | 19 Aug | 20 Aug
1 | T4 | Harden extraction, wire the Batch path | A dry-run batch of 20 papers submits, completes and reconciles by custom_id with zero schema failures. | 1 | 21 Aug | 21 Aug | bar: D5
2 | T5 | Batch-extract the 1,382 digital papers | ≥ 95% of papers land with a complete question set. The remainder are named in a failure report with their error class, not silently dropped. | 1 | 24 Aug | 24 Aug | Batch turnaround runs overnight — developer time is submission and reconciliation, not waiting.
2 | T6 | OCR route for the 69 scanned papers | All 69 papers extracted. A gates report per paper; any book-level page-count mismatch blocks that paper rather than passing degraded text downstream. | 2 | 25 Aug | 26 Aug | bar: D7 to D8
2 | T7 | Chunk and embed the 38 textbooks | Every chapter that has textbook pages has at least one chunk. Chapters with none are listed by name — a visible gap, not a silent one. | 1 | 27 Aug | 27 Aug | Batch job, overlaps T5/T6.
3 | T8 | Stratified review of extraction quality | A measured extraction error rate per axis, with any systematic failure mode fixed and its papers re-run. This number is the honest answer to 'can we trust the bank'. | 1 | 28 Aug | 28 Aug | Needs a reviewer for syllBIUS | bar: D10
3 | T9 | Retrieval evaluation and threshold tuning | Thresholds set from a measured precision/recall curve. Crucially: measured false-answer rate — how often a tier fires on the wrong chapter — because that is worse than a refusal. | 1 | 31 Aug | 31 Aug
3 | T10 | Tutor end-to-end verification | Every message carries its tier, similarity and cited sources. A deliberately unanswerable question produces a refusal naming what the programme does cover — not an invented answer. | 1 | 01 Sep | 01 Sep | bar: D12
3 | T11 | Grading calibration against known marks | Criterion-level agreement measured and reported. `tallyMarks` confirmed to exclude unmarked answers from both the awarded and available totals, and from mastery. | 1 | 02 Sep | 02 Sep
3 | T12 | Buffer and regression | Audit clean, tests green, no null-vector rows, extraction failure report empty or explained. | 2 | 03 Sep | 04 Sep | Deliberate slack — 13 days of work scheduled across 15. | bar: D14 to D15
TOTAL — 13 days of work scheduled across 15 (2 days deliberate slack)

## 3. The datasets (2)
The datasets
What the system is built on, and the state of each one today.
Inventory
Dataset | What it is | Size | State today
Past exam papers | Real Baccalaureate examinations as sat, published by the ministry, most with the official marking scheme. All four branches, both sessions per year. | 1,451 papers · 7,472 pages 2004–2021 · 110 sessions | COLLECTED — PROCESSING
— by branch | Literature & Humanities 520 · General Sciences 430 · Life Sciences 258 · Sociology & Economics 243. | 1,451 papers | Balanced
— by format | 1,382 are digital PDFs with extractable text. 69 are scans requiring OCR and confidence gating before any extraction. | 1,382 digital · 69 scanned | Two routes: T5 and T6
— with marking schemes | Papers carrying the official barème. These are what make defensible marking possible; the rest still yield questions and model answers. | 459 papers | Highest-value subset
— subjects | Mathematics, Physics, Chemistry, Biology, Philosophy, Arabic, French, English, History, Geography, Economics, Sociology, Civics — in Arabic, French and English versions. | ~15 subject areas × 3 languages | Complete
— known gap | No papers for the 2010, 2014 or 2020 sessions. 15 of 18 years covered. | 3 years missing | GAP — worth chasing
CRDP textbooks | The official course books, already transcribed to machine-readable text with mathematics as LaTeX and Arabic/French as Unicode. Every chapter carries the PDF page range it was read from, so any citation traces to a real page. | 38 books · 9,593 pages | TRANSCRIBED — not yet chunked
Curriculum map | Subjects, units and chapters parsed out of the textbooks' own contents pages by a regex parser — deliberately not a model, so the result is reproducible and reviewable. | 577 chapters GS 148 · LS 190 · SE 127 · LH 112 | LOADED — 6 books outstanding
Student work | Attempts, answers and photographed scripts. Feeds grading calibration and, at volume, difficulty recalibration. | None yet | ARRIVES WITH THE PILOT
Sample handwritten scripts | Needed to prove the photo → OCR self-consistency gate → marking path on real Lebanese handwriting. | ~20–30 needed | TO BE COLLECTED
Legend
Done / verified
In progress / awaited
Gap or blocker
Informational

## 3. The datasets
The datasets
What the system is built on, and the state of each one today.
Inventory
Dataset | What it is | Size | State today
Past exam papers | Real Baccalaureate examinations as sat, published by the ministry, most with the official marking scheme. All four branches, both sessions per year. | 1,451 papers · 7,472 pages 2004–2021 · 110 sessions | COLLECTED — PROCESSING
— by branch | Literature & Humanities 520 · General Sciences 430 · Life Sciences 258 · Sociology & Economics 243. | 1,451 papers | Balanced
— by format | 1,382 are digital PDFs with extractable text. 69 are scans requiring OCR and confidence gating before any extraction. | 1,382 digital · 69 scanned | Two routes: T5 and T6
— with marking schemes | Papers carrying the official barème. These are what make defensible marking possible; the rest still yield questions and model answers. | 459 papers | Highest-value subset
— subjects | Mathematics, Physics, Chemistry, Biology, Philosophy, Arabic, French, English, History, Geography, Economics, Sociology, Civics — in Arabic, French and English versions. | ~15 subject areas × 3 languages | Complete
— known gap | No papers for the 2010, 2014 or 2020 sessions. 15 of 18 years covered. | 3 years missing | GAP — worth chasing
CRDP textbooks | The official course books, already transcribed to machine-readable text with mathematics as LaTeX and Arabic/French as Unicode. Every chapter carries the PDF page range it was read from, so any citation traces to a real page. | 38 books · 9,593 pages | TRANSCRIBED — not yet chunked
Curriculum map | Subjects, units and chapters parsed out of the textbooks' own contents pages by a regex parser — deliberately not a model, so the result is reproducible and reviewable. | 577 chapters GS 148 · LS 190 · SE 127 · LH 112 | LOADED — 6 books outstanding
Student work | Attempts, answers and photographed scripts. Feeds grading calibration and, at volume, difficulty recalibration. | None yet | ARRIVES WITH THE PILOT
Sample handwritten scripts | Needed to prove the photo → OCR self-consistency gate → marking path on real Lebanese handwriting. | ~20–30 needed | TO BE COLLECTED
Legend
Done / verified
In progress / awaited
Gap or blocker
Informational